## Sheet1
(A - Accountable, C- Contribute, R - Review)
No | Task Name | Start Date | End Date | % Completion | Rajat | Tanvi | James | Nicol | Kumar
1 | Dataset Finalization | 2019-03-23 | 2019-03-24 |  | C | C | C | C | C
2 | Choose the option (Clustering or Association Rule Mining or Collaborative Mining)
3 | Review CRISP DM Framework
4 | Identify CRISP DM Outline to follow in the project
5 | Business Understanding Writeup
6 | Data Understanding 1 Writeup
7 | Data Understanding 2 Writeup
8 | EDA
9 | Data Cleanup
10 | Data Visualization
11 | Finalize the dataframe for modelling
12 | Check-in the code for data set / data frame
13 | Finalize validation strategy for the models
14 | Finalize the metirc for model performance
16 | Explore methodology for model
17 | Review methodology with the team
18 | Train and adjust parameters for model
19 | Evaluate and finalize the hyperparameters (if applicable)
20 | Fit the model
21 | Visualization
22 | Check-in preliminary code
23 | Review the results with the team
24 | Run prediction (if applicable)
25 | Check-in final code
26 | Write up for Modelling and evaluation 1
27 | Write up for Modelling and evaluation 2
28 | Write up for Modelling and evaluation 3
29 | Write up for Modelling and evaluation 4
30 | Review write up for all Modelling and evaluation
31 | Finalize write up for all Modelling and evaluation
32 | Check-in final notebook for model
33 | Deloyment writepup
34 | Review of deployment write up
35 | Finalize deployment write up
36 | Initial notebook merge
37 | Prepare final submission notebook
38 | Review final submission notebook
39 | Submission